## Gridlock_Utilities_Resource_and
Project ID | Project Name | In-Service Date | Sponsor | Lineworkers Needed | Engineers Needed | Technicians Needed | Equipment Operators Needed | Safety Personnel Needed | Total Crew Needed | Bucket Trucks Needed | Digger Derricks Needed | Mobile Cranes Needed | Excavators Needed | Poles/Structures Needed | Conductor Needed (mi) | Transformers Needed | Breakers/Switches Needed | Reactors Needed | Estimated Duration (days) | Labor Cost ($) | Equipment/Machinery Cost ($) | Material Cost ($) | Logistics Cost ($) | Engineering/Admin Cost ($) | External Contract Cost ($) | Total Project Cost ($)
18492 | MITCHELL - NORTH TIFTON 230KV RECONDUCTOR | 2025-05-01 | GPC | 22 | 9 | 6 | 10 | 4 | 51 | 8 | 3 | 3 | 4 | 72 | 13.3 | 2 | 3 | 0 | 233 | 6666000 | 4248000 | 2415000 | 476000 | 1092000 | 3323000 | 18220000
19187 | GRID - BREMEN - CROOKED CREEK (APC) 115 KV PROJECT | 2025-06-01 | GPC | 12 | 3 | 5 | 3 | 2 | 25 | 6 | 2 | 1 | 3 | 42 | 9.4 | 2 | 2 | 0 | 173 | 2790000 | 1827000 | 1775000 | 451000 | 569000 | 1031000 | 8443000
18153 | GTC: BONAIRE PRI- ECHECONNEE 115 KV PARTIAL REBUILD | 2025-06-01 | GTC | 18 | 7 | 8 | 5 | 3 | 41 | 3 | 1 | 0 | 1 | 33 | 7 | 3 | 1 | 0 | 105 | 2859000 | 390000 | 1561000 | 379000 | 418000 | 932000 | 6539000
20590 | GTC: EATONTON PRIMARY - LICK CREEK 115KV LINE SWITCH REPLACEMENT | 2025-06-01 | GTC | 9 | 4 | 6 | 4 | 1 | 24 | 4 | 2 | 1 | 1 | 8 | 0.6 | 1 | 3 | 0 | 91 | 1251000 | 691000 | 565000 | 208000 | 359000 | 1370000 | 4444000
11821 | JESUP - LUDOWICI PRIMARY 115KV REBUILD | 2025-06-01 | GPC | 13 | 3 | 5 | 6 | 3 | 30 | 6 | 1 | 2 | 2 | 45 | 4.8 | 5 | 1 | 0 | 126 | 1966000 | 1403000 | 1716000 | 442000 | 400000 | 784000 | 6711000
13787 | MEAG: AULTMAN ROAD - BONAIRE PRIMARY 115 KV REBUILD | 2025-06-01 | MEAG | 18 | 5 | 6 | 7 | 5 | 41 | 7 | 2 | 2 | 2 | 54 | 12.5 | 1 | 3 | 0 | 188 | 5141000 | 2389000 | 2080000 | 495000 | 354000 | 2047000 | 12506000
20464 | NORCROSS 230KV BUS 1-3 SERIES BUS TIE BREAKER INSTALLATION | 2025-06-01 | GPC | 14 | 4 | 6 | 6 | 3 | 33 | 5 | 3 | 1 | 3 | 7 | 0.8 | 1 | 1 | 0 | 146 | 2607000 | 1578000 | 394000 | 333000 | 541000 | 2351000 | 7804000
19631 | PINE GROVE PRIMARY 115 KV DUAL STAGE CAPACITOR BANK | 2025-06-01 | GPC | 8 | 4 | 5 | 4 | 1 | 22 | 3 | 2 | 1 | 1 | 4 | 1.4 | 3 | 3 | 0 | 113 | 1315000 | 783000 | 1014000 | 244000 | 216000 | 582000 | 4154000
20067 | SAV: DEPTFORD - MAGNOLIA 115KV RECONDUCTOR | 2025-06-01 | SAV | 18 | 6 | 5 | 3 | 5 | 37 | 7 | 3 | 1 | 2 | 51 | 7.9 | 2 | 5 | 0 | 148 | 3488000 | 1673000 | 1917000 | 273000 | 417000 | 2326000 | 10094000
21046 | THALMANN AND COLERAIN 23O KV LINE RELAY PANEL UPGRADES | 2025-06-01 | GPC | 14 | 5 | 7 | 6 | 4 | 36 | 6 | 1 | 2 | 2 | 11 | 1.7 | 3 | 4 | 0 | 139 | 3107000 | 1548000 | 1166000 | 482000 | 735000 | 1706000 | 8744000
18889 | JEFFERSON STREET#3 - NORTHWEST (WHITE) 115 KV RECONDUCTOR | 2025-12-01 | GPC | 15 | 7 | 5 | 8 | 3 | 38 | 6 | 3 | 1 | 3 | 36 | 4.1 | 6 | 2 | 0 | 184 | 4524000 | 2110000 | 1887000 | 355000 | 643000 | 1497000 | 11016000
20326 | ANTHONY SHOALS STATCOM SYSTEM | 2025-12-31 | GPC | 14 | 4 | 9 | 4 | 2 | 33 | 4 | 2 | 0 | 1 | 12 | 1.9 | 6 | 1 | 0 | 156 | 3212000 | 824000 | 1462000 | 233000 | 746000 | 1267000 | 7744000
20010 | GTC: ANTHONY SHOALS - WASHINGTON 115 KV LINE REBUILD | 2025-12-31 | GTC | 17 | 3 | 9 | 3 | 3 | 35 | 3 | 1 | 2 | 1 | 46 | 4.6 | 5 | 5 | 0 | 109 | 2159000 | 908000 | 2076000 | 396000 | 527000 | 1024000 | 7090000
17075 | SAV: LITTLE OGEECHEE 230- 115KV: RELAY MODERNIZATION | 2025-12-31 | SAV | 7 | 2 | 3 | 4 | 1 | 17 | 3 | 1 | 1 | 1 | 6 | 1.1 | 1 | 3 | 0 | 118 | 1240000 | 711000 | 616000 | 172000 | 378000 | 1418000 | 4535000
18960 | BLANKETS CREEK – WOODSTOCK 115KV LINE REBUILD | 2026-06-01 | GPC | 13 | 3 | 7 | 7 | 5 | 35 | 6 | 1 | 1 | 1 | 47 | 3.8 | 6 | 5 | 0 | 104 | 2180000 | 832000 | 2172000 | 384000 | 739000 | 2013000 | 8320000
20491 | EAST POINT RELAY MODERNIZATION | 2026-06-01 | GPC | 10 | 2 | 5 | 4 | 3 | 24 | 2 | 1 | 1 | 1 | 8 | 1.6 | 1 | 3 | 0 | 68 | 1095000 | 365000 | 680000 | 163000 | 200000 | 915000 | 3418000
20516 | GOAT ROCK 230KV SWITCH, JUMPER, & LINE TRAP REPLACEMENT | 2026-06-01 | GPC | 13 | 5 | 5 | 7 | 4 | 34 | 3 | 1 | 2 | 2 | 11 | 2.4 | 1 | 3 | 0 | 169 | 3419000 | 1548000 | 781000 | 233000 | 710000 | 2150000 | 8841000
19618 | GORDON-N DUBLIN 115KV (GORDON-ENGL MCI J) REBUILD | 2026-06-01 | GPC | 12 | 3 | 9 | 3 | 2 | 29 | 5 | 3 | 1 | 1 | 53 | 8 | 2 | 5 | 0 | 170 | 2919000 | 1557000 | 1935000 | 436000 | 750000 | 2151000 | 9748000
21139 | GRADY - MORROW (WHITE) 115KV REBUILD | 2026-06-01 | GPC | 21 | 3 | 6 | 5 | 5 | 40 | 3 | 3 | 0 | 1 | 48 | 7.6 | 3 | 5 | 0 | 121 | 3286000 | 669000 | 2058000 | 433000 | 472000 | 1921000 | 8839000
19706 | GRID - GAINESVILLE #2 EQUIPMENT REPLACEMENT | 2026-06-01 | GPC | 13 | 5 | 4 | 4 | 4 | 30 | 6 | 1 | 1 | 1 | 48 | 6.3 | 2 | 1 | 0 | 152 | 2440000 | 1216000 | 1343000 | 255000 | 453000 | 692000 | 6399000
19334 | GTC: LAGRANGE - NORTH OPELIKA 230 KV | 2026-06-01 | GTC | 19 | 7 | 7 | 10 | 6 | 49 | 6 | 3 | 1 | 4 | 30 | 14.7 | 7 | 3 | 0 | 182 | 4905000 | 2237000 | 3366000 | 382000 | 893000 | 2049000 | 13832000
19999 | GTC: ROBINS SPRING BUS REPLACEMENT | 2026-06-01 | GTC | 16 | 4 | 5 | 5 | 3 | 33 | 5 | 1 | 0 | 1 | 50 | 9.2 | 1 | 1 | 0 | 99 | 2124000 | 498000 | 1498000 | 457000 | 718000 | 1490000 | 6785000
20001 | GTC: ROBINS SPRING CAPACITOR BANK INSTALLATION | 2026-06-01 | GTC | 13 | 4 | 6 | 6 | 3 | 32 | 3 | 3 | 2 | 2 | 3 | 0.6 | 5 | 3 | 0 | 111 | 2231000 | 1218000 | 1289000 | 320000 | 610000 | 1955000 | 7623000
20490 | KLONDIKE RELAY MODERNIZATION | 2026-06-01 | GPC | 9 | 4 | 6 | 2 | 2 | 23 | 4 | 1 | 1 | 1 | 9 | 1.4 | 1 | 1 | 0 | 115 | 1386000 | 768000 | 470000 | 196000 | 402000 | 881000 | 4103000
19598 | MEAG: DRESDEN - LAGRANGE PRIMARY 230KV UPGRADE & JUMPERS | 2026-06-01 | MEAG | 16 | 6 | 6 | 4 | 2 | 34 | 5 | 1 | 2 | 3 | 10 | 2.3 | 3 | 2 | 0 | 157 | 3267000 | 1774000 | 1042000 | 261000 | 694000 | 2460000 | 9498000
20270 | MEAG: RAY PLACE RD - WASHINGTON #3 | 2026-06-01 | MEAG | 14 | 5 | 4 | 6 | 4 | 33 | 3 | 1 | 1 | 2 | 19 | 4.4 | 2 | 3 | 0 | 100 | 1878000 | 685000 | 1222000 | 459000 | 325000 | 1768000 | 6337000
20271 | MEAG: RAY PLACE RD - WASHINGTON (WASHINGTON - WASHINGTON 3) | 2026-06-01 | MEAG | 12 | 6 | 6 | 3 | 4 | 31 | 3 | 3 | 2 | 2 | 30 | 7.8 | 4 | 4 | 0 | 106 | 2182000 | 1163000 | 2113000 | 352000 | 389000 | 2189000 | 8388000
20300 | MORROW 115KV RELAY UPGRADE | 2026-06-01 | GPC | 9 | 2 | 6 | 5 | 2 | 24 | 2 | 2 | 1 | 1 | 9 | 1.4 | 1 | 2 | 0 | 80 | 1146000 | 502000 | 565000 | 317000 | 538000 | 710000 | 3778000
20066 | SAV: BOULEVARD - DEPTFORD 115KV RECONDUCTOR | 2026-06-01 | SAV | 21 | 3 | 9 | 5 | 2 | 40 | 3 | 2 | 2 | 2 | 26 | 7 | 1 | 5 | 0 | 107 | 2748000 | 1077000 | 1548000 | 536000 | 844000 | 1300000 | 8053000
20277 | SAV: MCINTOSH - PURRYSBURG 230KV REACTORS | 2026-06-01 | SAV | 22 | 8 | 11 | 10 | 6 | 57 | 5 | 3 | 1 | 3 | 13 | 2.1 | 1 | 3 | 5 | 210 | 7601000 | 2270000 | 2503000 | 582000 | 491000 | 1324000 | 14771000
17900 | UNION CITY - YATES 230 KV WHITE LINE REBUILD | 2026-04-01 | GPC | 17 | 4 | 13 | 8 | 4 | 46 | 10 | 3 | 0 | 4 | 65 | 11.7 | 5 | 4 | 0 | 208 | 6334000 | 2625000 | 2858000 | 792000 | 657000 | 1964000 | 15230000
20691 | UNION CITY - YATES 230KV (WHITE) SWITCH AND TRAP REPLACEMENT | 2026-06-01 | GPC | 13 | 6 | 6 | 7 | 3 | 35 | 4 | 3 | 1 | 1 | 14 | 1.8 | 1 | 3 | 0 | 173 | 3954000 | 1470000 | 722000 | 262000 | 429000 | 1515000 | 8352000
20223 | CC - PROJECT PAYTON BAINBRIDGE | 2026-06-30 | GPC | 20 | 4 | 9 | 8 | 3 | 44 | 8 | 4 | 3 | 3 | 47 | 9.3 | 1 | 3 | 0 | 170 | 4862000 | 3114000 | 1690000 | 499000 | 434000 | 2395000 | 12994000
20874 | GTC: BARNESVILLE PRIMARY- BARNESVILLE #1 115KV RECONDUCTOR | 2026-12-01 | GTC | 12 | 5 | 8 | 8 | 5 | 38 | 6 | 3 | 1 | 1 | 26 | 8.2 | 3 | 5 | 0 | 123 | 2454000 | 1208000 | 2056000 | 237000 | 840000 | 1478000 | 8273000
20002 | GTC: GORDON - SANDERSVILLE #1 115KV LINE REBUILD | 2026-12-01 | GTC | 16 | 7 | 5 | 6 | 5 | 39 | 6 | 2 | 2 | 1 | 39 | 7.5 | 2 | 5 | 0 | 140 | 2850000 | 1571000 | 1832000 | 480000 | 583000 | 1938000 | 9254000
19363 | MORROW - MOUNTAIN VIEW 115 KV REBUILD | 2026-12-31 | GPC | 12 | 6 | 8 | 7 | 2 | 35 | 6 | 1 | 1 | 2 | 48 | 6.8 | 5 | 3 | 0 | 180 | 3969000 | 1589000 | 2146000 | 415000 | 653000 | 2565000 | 11337000
20509 | CC - EMBLEM RIVERSIDE CUSTOMER SUB (FLEXENTIAL) | 2027-03-01 | GPC | 10 | 3 | 8 | 6 | 4 | 31 | 6 | 1 | 0 | 1 | 41 | 9.8 | 1 | 4 | 0 | 93 | 1764000 | 529000 | 1823000 | 464000 | 740000 | 2258000 | 7578000
19601 | MORROW - YATES COMMON 115KV LINE UPGRADE | 2027-05-01 | GPC | 12 | 3 | 5 | 3 | 2 | 25 | 6 | 2 | 2 | 2 | 23 | 7.4 | 4 | 2 | 0 | 167 | 2225000 | 2012000 | 1855000 | 244000 | 740000 | 1894000 | 8970000
15879 | POSSUM BRANCH - YATES COMMON 115KV REBUILD (YATES TO CLEM) | 2027-05-01 | GPC | 21 | 5 | 6 | 5 | 5 | 42 | 6 | 3 | 2 | 1 | 34 | 4.5 | 5 | 3 | 0 | 119 | 3249000 | 1443000 | 1836000 | 341000 | 574000 | 2490000 | 9933000
20736 | CC - TA REALTY ELLENWOOD NETWORK IMPROVEMENTS | 2027-06-01 | GPC | 10 | 3 | 5 | 4 | 4 | 26 | 5 | 2 | 1 | 1 | 34 | 10.7 | 2 | 2 | 0 | 140 | 1991000 | 1155000 | 1899000 | 215000 | 606000 | 1020000 | 6886000
20234 | DOYLE - LG&E MONROE 230KV - JACKS CREEK LOOP IN | 2027-06-01 | GPC | 19 | 7 | 9 | 9 | 4 | 48 | 4 | 3 | 3 | 3 | 45 | 13 | 7 | 4 | 0 | 194 | 5950000 | 2865000 | 3314000 | 392000 | 997000 | 2462000 | 15980000
20778 | GTC: DOYLE - WINDER PRIMARY 230KV LINE JUMPER REPLACEMENT | 2027-06-01 | GTC | 17 | 4 | 5 | 3 | 4 | 33 | 6 | 3 | 2 | 2 | 6 | 1.4 | 2 | 1 | 0 | 115 | 2254000 | 1490000 | 645000 | 481000 | 533000 | 1000000 | 6403000
19358 | GTC: EAST MOULTRIE - HIGHWAY 112 230 KV LINE | 2027-06-01 | GTC | 26 | 7 | 6 | 10 | 4 | 53 | 7 | 4 | 1 | 3 | 52 | 6.7 | 3 | 4 | 0 | 176 | 5886000 | 2294000 | 1872000 | 374000 | 723000 | 3109000 | 14258000
20020 | GTC: SOUTH HAZLEHURST - NEW LACY 230KV LINE | 2027-06-01 | GTC | 25 | 9 | 10 | 6 | 6 | 56 | 6 | 3 | 0 | 1 | 51 | 11.9 | 3 | 3 | 0 | 162 | 5978000 | 1216000 | 2372000 | 606000 | 566000 | 2025000 | 12763000
18668 | JESUP - OFFERMAN 115KV REBUILD | 2027-06-01 | GPC | 15 | 3 | 7 | 6 | 5 | 36 | 7 | 3 | 1 | 3 | 37 | 5.9 | 5 | 1 | 0 | 146 | 3080000 | 1771000 | 1817000 | 479000 | 404000 | 1893000 | 9444000
10143 | LAWRENCEVILLE - WINDER 115KV LINE REBUILD | 2027-06-01 | GPC | 12 | 7 | 5 | 3 | 2 | 29 | 6 | 2 | 1 | 2 | 51 | 6.4 | 6 | 3 | 0 | 160 | 2886000 | 1558000 | 2294000 | 444000 | 658000 | 815000 | 8655000
10481 | LAWRENCEVILLE - WINDER PRIMARY 230KV LINE REBUILD | 2027-06-01 | GPC | 27 | 6 | 6 | 10 | 6 | 55 | 5 | 4 | 0 | 3 | 72 | 8.6 | 5 | 3 | 0 | 164 | 5728000 | 1542000 | 2429000 | 448000 | 647000 | 2935000 | 13729000
20264 | MEAG: RAY PLACE RD - WARRENTON PRIMARY | 2027-06-01 | MEAG | 13 | 6 | 4 | 5 | 4 | 32 | 5 | 3 | 1 | 1 | 53 | 4.8 | 3 | 1 | 0 | 123 | 2503000 | 1126000 | 1372000 | 289000 | 295000 | 1396000 | 6981000
19248 | SANDERSVILLE #1 - WADLEY PRI. 115KV REBUILD/RECONDUCTOR | 2027-06-01 | GPC | 17 | 7 | 7 | 3 | 5 | 39 | 7 | 2 | 0 | 2 | 54 | 5 | 1 | 5 | 0 | 142 | 3234000 | 1148000 | 1408000 | 391000 | 622000 | 933000 | 7736000
20785 | SAV: GOSHEN (SAV) - KRAFT 115KV LINE REBUILD | 2027-06-01 | SAV | 21 | 5 | 9 | 8 | 5 | 48 | 3 | 1 | 2 | 2 | 57 | 4.7 | 3 | 5 | 0 | 152 | 4509000 | 1392000 | 1753000 | 395000 | 841000 | 2223000 | 11113000
20065 | SAV: GOSHEN (SAV) - MCINTOSH 115KV LINE REBUILD | 2027-06-01 | SAV | 14 | 5 | 8 | 5 | 2 | 34 | 7 | 3 | 2 | 3 | 37 | 4.7 | 1 | 5 | 0 | 146 | 2606000 | 2108000 | 1319000 | 548000 | 626000 | 1231000 | 8438000
18573 | GRID - ARKWRIGHT - LLOYD SHOALS 115KV | 2027-07-30 | GPC | 17 | 4 | 4 | 7 | 3 | 35 | 6 | 3 | 1 | 1 | 25 | 10.9 | 2 | 3 | 0 | 162 | 3107000 | 1590000 | 1988000 | 182000 | 713000 | 2122000 | 9702000
20591 | GTC: EATONTON PRIMARY (035591) - LICK CREEK 115KV REBUILD | 2027-12-01 | GTC | 18 | 6 | 9 | 3 | 2 | 38 | 7 | 2 | 0 | 2 | 31 | 10.9 | 5 | 3 | 0 | 113 | 2314000 | 914000 | 2563000 | 245000 | 485000 | 851000 | 7372000
17977 | ATHENA - EAST WATKINSVILLE 115 KV (REBUILD) | 2027-12-31 | GPC | 18 | 7 | 6 | 3 | 5 | 39 | 6 | 1 | 0 | 3 | 46 | 11.1 | 2 | 3 | 0 | 150 | 3797000 | 1101000 | 2079000 | 263000 | 771000 | 1530000 | 9541000
08458 | GTC: BARNESVILLE - SOUTH GRIFFIN 230KV PROJECT | 2028-06-01 | GTC | 16 | 7 | 7 | 10 | 4 | 44 | 7 | 1 | 0 | 1 | 52 | 10.2 | 1 | 6 | 0 | 214 | 5245000 | 1359000 | 2094000 | 677000 | 881000 | 2347000 | 12603000
20503 | GTC: BARNEYVILLE - EAST MOULTRIE 115KV NEW LINE | 2028-06-01 | GTC | 18 | 8 | 5 | 7 | 5 | 43 | 4 | 3 | 1 | 1 | 58 | 5.9 | 5 | 5 | 0 | 152 | 4386000 | 1292000 | 2264000 | 353000 | 891000 | 2925000 | 12111000
20873 | GTC: BONAIRE PRIMARY 500/230KV XFMR REPLCMNT & RELAY MOD | 2028-06-01 | GTC | 15 | 5 | 9 | 4 | 3 | 36 | 8 | 1 | 1 | 1 | 2 | 0.6 | 6 | 1 | 0 | 178 | 3396000 | 1659000 | 1280000 | 352000 | 650000 | 835000 | 8172000
19629 | MEAG: BRUMBLEY CREEK - SOUTH BAINBRIDGE 115KV REBUILD | 2028-06-01 | MEAG | 13 | 3 | 5 | 8 | 3 | 32 | 7 | 3 | 0 | 2 | 26 | 8.1 | 3 | 5 | 0 | 103 | 1852000 | 926000 | 2045000 | 242000 | 553000 | 1204000 | 6822000
20656 | PLANT YATES BREAKER AND HALF STATION | 2028-06-01 | GPC | 13 | 3 | 3 | 2 | 2 | 23 | 3 | 1 | 0 | 1 | 9 | 1.1 | 3 | 3 | 0 | 138 | 1812000 | 512000 | 995000 | 285000 | 221000 | 915000 | 4740000
20783 | SAV: COLEMAN - DEAN FOREST 115KV LINE REBUILD | 2028-06-01 | SAV | 16 | 7 | 7 | 7 | 3 | 40 | 6 | 3 | 1 | 1 | 40 | 5.9 | 2 | 3 | 0 | 118 | 2714000 | 1158000 | 1462000 | 423000 | 430000 | 1427000 | 7614000
20407 | SAV: MAGNOLIA - TRUMAN PARKWAY 115KV REBUILD | 2028-06-01 | SAV | 18 | 3 | 7 | 6 | 5 | 39 | 6 | 2 | 0 | 2 | 46 | 10.9 | 2 | 1 | 0 | 103 | 2406000 | 765000 | 1866000 | 471000 | 305000 | 2577000 | 8390000
20768 | SOUTH MACON 115KV BUSES 1 & 2 REPLACEMENT | 2028-06-01 | GPC | 16 | 4 | 8 | 3 | 2 | 33 | 3 | 1 | 2 | 1 | 32 | 3.4 | 5 | 3 | 0 | 158 | 3509000 | 1317000 | 1703000 | 233000 | 304000 | 1395000 | 8461000
20274 | UNION CITY - YATES 230KV (BLACK) LINE REBUILD | 2028-06-01 | GPC | 25 | 8 | 8 | 6 | 3 | 50 | 5 | 2 | 3 | 4 | 53 | 13.2 | 6 | 6 | 0 | 198 | 6178000 | 3038000 | 3368000 | 740000 | 450000 | 2562000 | 16336000
10222 | BLAKELY PRIMARY - HUCKLEBERRY 115KV REBUILD | 2029-06-01 | GPC | 21 | 6 | 8 | 5 | 3 | 43 | 7 | 1 | 2 | 1 | 56 | 12.2 | 3 | 3 | 0 | 142 | 3871000 | 1558000 | 2422000 | 341000 | 417000 | 2372000 | 10981000
16887 | BUTLER - THOMASTON 230KV LINE CONVERSION | 2029-06-01 | GPC | 27 | 6 | 8 | 10 | 3 | 54 | 10 | 4 | 1 | 3 | 78 | 12.9 | 6 | 4 | 0 | 173 | 5512000 | 2598000 | 3223000 | 315000 | 1016000 | 2221000 | 14885000
21142 | CONYERS - KLONDIKE 230 KV SECOND LINE | 2029-06-01 | GPC | 33 | 8 | 8 | 10 | 6 | 65 | 10 | 4 | 3 | 1 | 98 | 13.2 | 3 | 3 | 0 | 219 | 7559000 | 3939000 | 2672000 | 509000 | 922000 | 3822000 | 19423000
21138 | GLENWOOD SPRINGS - PORTERDALE PRIMARY 230KV LINE SWITCH REPL | 2029-06-01 | GPC | 14 | 3 | 7 | 7 | 3 | 34 | 3 | 3 | 0 | 3 | 8 | 2.3 | 1 | 1 | 0 | 94 | 1767000 | 675000 | 570000 | 429000 | 588000 | 2200000 | 6229000
21112 | GTC: BARNESVILLE PRIMARY - THOMASTON 230KV | 2029-06-01 | GTC | 17 | 7 | 10 | 6 | 6 | 46 | 7 | 1 | 0 | 1 | 48 | 5 | 6 | 1 | 0 | 134 | 3440000 | 851000 | 1934000 | 347000 | 807000 | 1350000 | 8729000
10814 | GTC: BAY CREEK 230/115KV SECOND AUTO TRANSFORMER | 2029-06-01 | GTC | 17 | 4 | 7 | 6 | 5 | 39 | 5 | 4 | 1 | 4 | 19 | 2.9 | 2 | 4 | 0 | 159 | 3386000 | 1994000 | 1144000 | 468000 | 460000 | 2661000 | 10113000
21140 | GTC: BONAIRE PRIMARY - EASTMAN PRIMARY 115 KV LINE REBUILD | 2029-06-01 | GTC | 15 | 7 | 5 | 5 | 5 | 37 | 6 | 1 | 1 | 1 | 31 | 12.2 | 1 | 2 | 0 | 150 | 3125000 | 1200000 | 1877000 | 491000 | 376000 | 2788000 | 9857000
20760 | GTC: HOPEWELL 230/115 KV BANK A | 2029-06-01 | GTC | 22 | 7 | 8 | 4 | 2 | 43 | 4 | 1 | 1 | 4 | 22 | 3.3 | 5 | 5 | 0 | 151 | 4376000 | 1383000 | 1850000 | 337000 | 540000 | 1977000 | 10463000
21141 | LLOYD SHOALS - PORTERDALE PRIMARY 115KV REBUILD | 2029-06-01 | GPC | 14 | 3 | 9 | 7 | 5 | 38 | 7 | 1 | 0 | 2 | 59 | 7.9 | 3 | 1 | 0 | 156 | 3735000 | 1120000 | 1747000 | 246000 | 690000 | 922000 | 8460000
19621 | MCEVER ROAD - SHOAL CREEK 115KV REBUILD | 2029-06-01 | GPC | 21 | 3 | 6 | 8 | 3 | 41 | 7 | 3 | 2 | 1 | 25 | 11.8 | 1 | 5 | 0 | 124 | 2964000 | 1586000 | 2097000 | 439000 | 767000 | 859000 | 8712000
20346 | MCMANUS - WEST BRUNSWICK 115KV REBUILD | 2029-06-01 | GPC | 15 | 6 | 5 | 7 | 3 | 36 | 3 | 1 | 1 | 2 | 31 | 5.8 | 5 | 2 | 0 | 184 | 4233000 | 1260000 | 1881000 | 349000 | 328000 | 1826000 | 9877000
20757 | NORCROSS - NORTH DRUID HILLS 115KV REBUILD | 2029-06-01 | GPC | 14 | 7 | 8 | 7 | 3 | 39 | 7 | 2 | 2 | 3 | 46 | 7 | 5 | 2 | 0 | 134 | 3548000 | 1813000 | 2067000 | 392000 | 461000 | 812000 | 9093000
21006 | SAV: BOULEVARD - MAGNOLIA 115 KV LINE REBUILD | 2029-06-01 | SAV | 13 | 3 | 6 | 7 | 5 | 34 | 7 | 1 | 1 | 3 | 57 | 6.9 | 1 | 1 | 0 | 158 | 3046000 | 1629000 | 1256000 | 329000 | 606000 | 2400000 | 9266000
21023 | SAV: DEAN FOREST - LITTLE OGEECHEE 230 KV REBUILD | 2029-06-01 | SAV | 30 | 4 | 10 | 8 | 6 | 58 | 6 | 2 | 3 | 3 | 58 | 14.2 | 3 | 3 | 0 | 240 | 7990000 | 3643000 | 2659000 | 553000 | 1201000 | 3186000 | 19232000
13628 | SOUTH BAINBRIDGE - SINAI (FPL) 115KV LINE RECONDUCTOR | 2029-06-01 | GPC | 16 | 5 | 7 | 5 | 3 | 36 | 3 | 2 | 1 | 1 | 22 | 3.9 | 1 | 1 | 0 | 105 | 2011000 | 728000 | 799000 | 431000 | 407000 | 2044000 | 6420000
20248 | BAY CREEK - CONYERS 230KV REBUILD | 2029-12-31 | GPC | 27 | 8 | 10 | 8 | 3 | 56 | 5 | 3 | 3 | 4 | 37 | 5.1 | 8 | 3 | 0 | 190 | 6363000 | 3088000 | 2470000 | 393000 | 541000 | 2085000 | 14940000
18669 | DU: DAWSON CROSSING - NELSON (WHITE) 115 KV REBUILD | 2030-06-01 | DU | 13 | 7 | 8 | 5 | 5 | 38 | 7 | 2 | 2 | 1 | 39 | 5.5 | 2 | 1 | 0 | 162 | 4008000 | 1925000 | 1222000 | 556000 | 856000 | 1142000 | 9709000
21097 | EAST POINT - TRIBUTARY 230KV REBUILD | 2030-06-01 | GPC | 30 | 8 | 6 | 10 | 3 | 57 | 10 | 4 | 1 | 3 | 83 | 17.5 | 2 | 3 | 0 | 234 | 8310000 | 3514000 | 2933000 | 441000 | 558000 | 1148000 | 16904000
20480 | EAST POINT - UNION CITY 230KV BLACK LINE RECONDUCTOR | 2030-06-01 | GPC | 18 | 9 | 6 | 4 | 3 | 40 | 6 | 3 | 1 | 3 | 83 | 10.5 | 5 | 6 | 0 | 156 | 3532000 | 1789000 | 2968000 | 373000 | 890000 | 1122000 | 10674000
12120 | GAINESVILLE #2 - MCEVER ROAD 115 KV REBUILD | 2030-06-01 | GPC | 14 | 5 | 9 | 8 | 5 | 41 | 6 | 3 | 1 | 1 | 54 | 5.4 | 6 | 1 | 0 | 146 | 3316000 | 1433000 | 1999000 | 333000 | 492000 | 1697000 | 9270000
20298 | GLENWOOD SPRINGS - LAKE OCONEE 115KV LINE REBUILD | 2030-06-01 | GPC | 16 | 6 | 8 | 5 | 5 | 40 | 6 | 3 | 2 | 1 | 34 | 7.1 | 1 | 1 | 0 | 192 | 4209000 | 2328000 | 1205000 | 217000 | 357000 | 749000 | 9065000
21128 | GOAT ROCK REACTORS INSTALLATION | 2030-06-01 | GPC | 15 | 6 | 9 | 6 | 4 | 40 | 8 | 1 | 1 | 4 | 7 | 1.1 | 3 | 2 | 5 | 138 | 3097000 | 1628000 | 2644000 | 301000 | 763000 | 1998000 | 10431000
19996 | GOLDENS CREEK - WARRENTON PRIMARY 230KV REBUILD | 2030-06-01 | GPC | 22 | 6 | 11 | 8 | 6 | 53 | 8 | 3 | 3 | 4 | 58 | 13.4 | 8 | 6 | 0 | 161 | 5717000 | 2935000 | 3777000 | 323000 | 882000 | 3432000 | 17066000
20428 | GORDON-SANDERSVILLE #1 115KV LINE REBUILD (DEEPSTEP-SAND #6) | 2030-06-01 | GPC | 13 | 5 | 6 | 5 | 2 | 31 | 5 | 1 | 1 | 2 | 30 | 7.6 | 5 | 3 | 0 | 140 | 2721000 | 1143000 | 2180000 | 318000 | 297000 | 2349000 | 9008000
21116 | GOSHEN AREA STRATEGIC SOLUTION | 2030-06-01 | GPC | 18 | 3 | 6 | 5 | 2 | 34 | 6 | 1 | 2 | 2 | 36 | 9.4 | 3 | 2 | 0 | 175 | 3957000 | 1949000 | 1941000 | 331000 | 390000 | 1983000 | 10551000
21073 | GTC: BIG SMARR - TOMOCHICHI 500KV | 2030-06-01 | GTC | 28 | 8 | 10 | 9 | 6 | 61 | 5 | 4 | 1 | 1 | 46 | 16 | 3 | 6 | 0 | 178 | 6015000 | 1792000 | 3112000 | 685000 | 469000 | 3180000 | 15253000
20375 | GTC: EAST WATKINSVILLE 230 KV STATION MODIFICATION | 2030-06-01 | GTC | 17 | 9 | 10 | 4 | 6 | 46 | 9 | 4 | 1 | 1 | 46 | 10.9 | 7 | 3 | 0 | 136 | 3954000 | 1728000 | 2981000 | 714000 | 851000 | 1036000 | 11264000
21077 | GTC: ROCKVILLE - TIGER CREEK -WARTHEN 500KV LINES | 2030-06-01 | GTC | 31 | 8 | 13 | 9 | 3 | 64 | 10 | 2 | 1 | 1 | 39 | 10.5 | 3 | 6 | 0 | 174 | 7417000 | 2010000 | 2457000 | 498000 | 1296000 | 1608000 | 15286000
21094 | GTC: TIGER CREEK- ROCKVILLE-NORTH SPA 230KV PROJECT | 2030-06-01 | GTC | 23 | 7 | 6 | 7 | 6 | 49 | 7 | 3 | 3 | 3 | 48 | 11.5 | 7 | 6 | 0 | 164 | 4653000 | 2747000 | 3341000 | 474000 | 503000 | 1372000 | 13090000
20789 | JEFFERSON ROAD - WINDER PRIMARY 115KV REBUILD | 2030-06-01 | GPC | 13 | 7 | 5 | 8 | 5 | 38 | 6 | 2 | 0 | 3 | 49 | 11.3 | 6 | 1 | 0 | 146 | 3673000 | 1204000 | 2661000 | 259000 | 780000 | 1551000 | 10128000
20284 | KETTLE CREEK PRIMARY - PINE GROVE PRIMARY 115KV REBUILD | 2030-06-01 | GPC | 16 | 7 | 9 | 5 | 3 | 40 | 6 | 2 | 0 | 1 | 32 | 8.6 | 5 | 5 | 0 | 174 | 4552000 | 1148000 | 2491000 | 212000 | 736000 | 761000 | 9900000
21118 | MEAG: ATHENA - WARRENTON 230KV CONVERSION | 2030-06-01 | MEAG | 17 | 8 | 11 | 9 | 3 | 48 | 8 | 2 | 1 | 1 | 80 | 17.5 | 6 | 2 | 0 | 150 | 3751000 | 1535000 | 3568000 | 482000 | 1089000 | 2309000 | 12734000
19995 | TALLULAH LODGE - TOCCOA 115 KV REBUILD | 2030-06-01 | GPC | 20 | 7 | 8 | 7 | 2 | 44 | 5 | 3 | 0 | 1 | 36 | 9.4 | 1 | 5 | 0 | 125 | 3130000 | 856000 | 1856000 | 320000 | 827000 | 1053000 | 8042000
20160 | THOMASTON 230 NEW BUILD SUB | 2030-11-01 | GPC | 19 | 8 | 11 | 4 | 3 | 45 | 5 | 1 | 1 | 4 | 55 | 4.8 | 3 | 3 | 0 | 136 | 4143000 | 1335000 | 1568000 | 667000 | 941000 | 1585000 | 10239000
18848 | BAINBRIDGE TRANSMISSION: EAST RIVER ROAD, EAST BAINBRIDGE | 2030-12-31 | GPC | 15 | 4 | 6 | 5 | 2 | 32 | 3 | 1 | 0 | 2 | 43 | 4.6 | 4 | 1 | 0 | 155 | 3224000 | 703000 | 1502000 | 397000 | 294000 | 2090000 | 8210000
19626 | GLENWOOD SPRINGS 115KV CAP BANK | 2030-12-31 | GPC | 9 | 4 | 4 | 4 | 2 | 23 | 4 | 1 | 1 | 1 | 7 | 0.8 | 1 | 3 | 0 | 123 | 1652000 | 822000 | 584000 | 357000 | 189000 | 734000 | 4338000
20690 | EAST POINT - UNION CITY (WHITE) 230KV REBUILD | 2031-05-01 | GPC | 30 | 8 | 6 | 10 | 4 | 58 | 8 | 2 | 1 | 3 | 60 | 9.4 | 5 | 3 | 0 | 232 | 7966000 | 2756000 | 2483000 | 828000 | 988000 | 2311000 | 17332000
19632 | AVERY - HOPEWELL 115KV RECONDUCTOR | 2031-06-01 | GPC | 15 | 7 | 5 | 3 | 3 | 33 | 3 | 3 | 2 | 3 | 53 | 4.5 | 5 | 2 | 0 | 182 | 3568000 | 2147000 | 1802000 | 481000 | 371000 | 2361000 | 10730000
10811 | BOWEN #10 500/230KV AUTOBANK REPLACEMENT | 2031-06-01 | GPC | 30 | 4 | 6 | 9 | 4 | 53 | 8 | 2 | 0 | 3 | 28 | 3.7 | 2 | 2 | 0 | 244 | 8522000 | 2335000 | 1075000 | 471000 | 1223000 | 3250000 | 16876000
20756 | HATCH - WADLEY 500 KV LINE STRATEGIC PROJECT | 2031-06-01 | GPC | 40 | 8 | 11 | 10 | 6 | 75 | 6 | 2 | 0 | 4 | 117 | 12 | 8 | 3 | 0 | 307 | 15381000 | 2786000 | 3519000 | 537000 | 1569000 | 2111000 | 25903000
21114 | MEAG: SOUTH GRIFFIN 230/115KV BANK #5 | 2032-06-01 | MEAG | 12 | 5 | 7 | 8 | 5 | 37 | 6 | 2 | 0 | 4 | 17 | 2.7 | 6 | 1 | 0 | 111 | 2608000 | 1007000 | 1570000 | 376000 | 745000 | 2454000 | 8760000
20784 | SAV: COLEMAN - MELDRIM 115KV LINE REBUILD | 2032-06-01 | SAV | 18 | 3 | 5 | 7 | 3 | 36 | 5 | 2 | 1 | 1 | 40 | 6 | 6 | 2 | 0 | 109 | 2178000 | 899000 | 2118000 | 370000 | 381000 | 2014000 | 7960000
20758 | BAY CREEK - CONYERS 230KV LIMITING ELEMENT REPLACEMENT | 2033-06-01 | GPC | 19 | 4 | 12 | 4 | 4 | 43 | 4 | 3 | 0 | 3 | 49 | 5.9 | 1 | 6 | 0 | 214 | 5751000 | 1677000 | 1590000 | 346000 | 570000 | 2011000 | 11945000
20793 | EVANS PRIMARY - THURMOND DAM (USA) #5 115KV REBUILD | 2033-06-01 | GPC | 16 | 5 | 8 | 6 | 2 | 37 | 6 | 3 | 2 | 1 | 55 | 11.1 | 5 | 2 | 0 | 122 | 2587000 | 1480000 | 2568000 | 246000 | 851000 | 1703000 | 9435000
20794 | EVANS PRIMARY - THURMOND DAM (USA) #6 115KV REBUILD | 2033-06-01 | GPC | 17 | 7 | 7 | 8 | 3 | 42 | 5 | 2 | 2 | 3 | 59 | 9.9 | 5 | 3 | 0 | 178 | 4590000 | 2173000 | 2537000 | 407000 | 550000 | 1000000 | 11257000
12217 | GTC: CENTER PRIMARY - CLARKSBORO 230 KV REBUILD | 2033-06-01 | GTC | 30 | 4 | 6 | 4 | 6 | 50 | 10 | 3 | 0 | 3 | 47 | 14.3 | 6 | 2 | 0 | 199 | 5552000 | 2348000 | 3095000 | 674000 | 532000 | 3649000 | 15850000
20773 | GTC: CLARKSBORO - WINDER PRIMARY 230KV REBUILD | 2033-06-01 | GTC | 25 | 4 | 13 | 4 | 6 | 52 | 8 | 4 | 3 | 3 | 50 | 8.9 | 8 | 3 | 0 | 202 | 7080000 | 3700000 | 2948000 | 625000 | 592000 | 3141000 | 18086000
12147 | GTC: EAST SOCIAL CIRCLE - SNELLVILLE 230KV EQUIPMENT UPGRADE | 2033-06-01 | GTC | 25 | 7 | 6 | 10 | 3 | 51 | 6 | 4 | 0 | 3 | 33 | 5.1 | 4 | 3 | 0 | 172 | 5860000 | 1731000 | 1717000 | 474000 | 433000 | 2456000 | 12671000
20791 | GTC: SHOAL CREEK - SOUTH HALL 230KV REBUILD | 2033-06-01 | GTC | 20 | 6 | 10 | 10 | 4 | 50 | 6 | 2 | 1 | 3 | 35 | 9.5 | 8 | 3 | 0 | 193 | 5829000 | 2038000 | 2970000 | 487000 | 507000 | 3403000 | 15234000
21053 | MCEVER ROAD - SHOAL CREEK 115KV REBUILD PHASE III | 2033-06-01 | GPC | 12 | 7 | 7 | 7 | 2 | 35 | 6 | 2 | 2 | 1 | 45 | 9.6 | 6 | 5 | 0 | 132 | 3091000 | 1481000 | 2833000 | 391000 | 374000 | 798000 | 8968000
20796 | SAV: MELDRIM BANK D REPLACEMENT | 2033-06-01 | SAV | 14 | 6 | 7 | 5 | 5 | 37 | 6 | 1 | 0 | 1 | 19 | 3 | 5 | 1 | 0 | 116 | 2494000 | 660000 | 1426000 | 264000 | 765000 | 2028000 | 7637000
14222 | THOMSON PRIMARY 230/115KV SECOND TRANSFORMER | 2033-06-01 | GPC | 22 | 5 | 8 | 4 | 5 | 44 | 5 | 4 | 2 | 1 | 17 | 1.4 | 2 | 1 | 0 | 126 | 3299000 | 1559000 | 680000 | 241000 | 661000 | 1650000 | 8090000
20759 | WINDER PRIMARY 230KV BUS 1-2 PARALLEL BUS-TIE INSTALLATION | 2033-06-01 | GPC | 26 | 7 | 7 | 9 | 6 | 55 | 6 | 3 | 3 | 3 | 49 | 9.1 | 7 | 4 | 0 | 144 | 4293000 | 2317000 | 2878000 | 665000 | 530000 | 3467000 | 14150000
10487 | PINE GROVE PRIMARY - WEST VALDOSTA 115 KV RECONDUCTOR | 2033-12-31 | GPC | 21 | 7 | 5 | 7 | 5 | 45 | 3 | 3 | 2 | 2 | 46 | 4.7 | 5 | 5 | 0 | 117 | 3249000 | 1284000 | 2088000 | 228000 | 471000 | 2700000 | 10020000
18700 | DAWSON CROSSING - GAINESVILLE #1 115 KV | 2034-06-01 | GPC | 17 | 4 | 8 | 4 | 3 | 36 | 5 | 3 | 2 | 1 | 34 | 4.7 | 5 | 2 | 0 | 120 | 2644000 | 1376000 | 1764000 | 399000 | 477000 | 899000 | 7559000
20787 | SAV: LITTLE OGEECHEE 230/115KV BANK REPLACEMENT | 2034-06-01 | SAV | 19 | 6 | 8 | 7 | 2 | 42 | 5 | 1 | 0 | 1 | 8 | 2.9 | 5 | 2 | 0 | 180 | 4914000 | 906000 | 1474000 | 249000 | 456000 | 2280000 | 10279000
17993 | EVANS PRIMARY - THOMSON PRIMARY 115KV REBUILD | 2034-12-31 | GPC | 18 | 6 | 5 | 5 | 2 | 36 | 6 | 1 | 0 | 2 | 22 | 8.9 | 1 | 2 | 0 | 152 | 3562000 | 991000 | 1469000 | 328000 | 807000 | 2270000 | 9427000

## Utility B Resources
Project ID | Project Name | In-Service Date | Status | Located Point | Latitude | Longitude | Center Latitude | Center Longitude | Lineworkers Needed | Engineers Needed | Technicians Needed | Equipment Operators Needed | Safety Personnel Needed | Total Crew Needed | Bucket Trucks Needed | Digger Derricks Needed | Mobile Cranes Needed | Excavators Needed | Poles/Structures Needed | Conductor Needed (mi) | Transformers Needed | Breakers/Switches Needed | Reactors Needed | Estimated Duration (days) | Labor Cost ($) | Equipment/Machinery Cost ($) | Material Cost ($) | Logistics Cost ($) | Engineering/Admin Cost ($) | External Contract Cost ($) | Total Project Cost ($)
0139 M,N | Okatie 230-115kV Substation, Jasper – Yemassee 230kV #1 Fold-in | 2024-12-31 | In Progress | Yemassee Substation | 32.6975 | -80.8639 | 32.6975 | -80.8639 | 33 | 6 | 6 | 9 | 3 | 57 | 10 | 2 | 3 | 3 | 58 | 10.1 | 5 | 3 | 0 | 218 | 7046000 | 3885000 | 2557000 | 612000 | 1349000 | 4143000 | 19592000
6341 A-F | Cainhoy - Hamlin 115kV: Rebuild Line and Cainhoy – Hamlin 115 kV #2: Construct New 115 kV Line | 2025-12-01 | In Progress | Cainhoy Substation | 32.9414 | -79.8423 | 32.9414 | -79.8423 | 23 | 7 | 9 | 7 | 3 | 49 | 7 | 1 | 3 | 4 | 47 | 12.3 | 7 | 6 | 0 | 236 | 7517000 | 3719000 | 3430000 | 572000 | 691000 | 2671000 | 18600000
6808 N,O | VCS1-Denny Terrace 230kV & VCS1-Pineland 230kV: Rebuild Single Circuit Sections | 2026-12-31 | In Progress | Denny Terrace Substation | 34.0576 | -81.0615 | 34.0576 | -81.0615 | 25 | 4 | 10 | 8 | 6 | 53 | 10 | 3 | 0 | 1 | 43 | 19.5 | 8 | 3 | 0 | 169 | 5168000 | 1715000 | 4145000 | 640000 | 1198000 | 2507000 | 15373000
6808 S | Okatie-Bluffton 115kV: Rebuild | 2025-06-01 | In Progress | Bluffton Substation | 32.235 | -80.8534 | 32.235 | -80.8534 | 17 | 6 | 7 | 5 | 2 | 37 | 7 | 3 | 1 | 2 | 60 | 11.2 | 6 | 2 | 0 | 173 | 3713000 | 1955000 | 2780000 | 262000 | 802000 | 2245000 | 11757000
06076A | Canadys-Ritter 115KV-Rebld SPDC 230/115KV 1272 (Approx 18 Miles) | 2026-06-01 | In Progress | Canadys Substation | 33.0641 | -80.6207 | 33.0641 | -80.6207 | 35 | 9 | 10 | 8 | 4 | 66 | 10 | 4 | 3 | 1 | 110 | 11.8 | 5 | 4 | 0 | 277 | 11865000 | 4982000 | 3014000 | 969000 | 1090000 | 2925000 | 24845000
6359 | Yemassee– Ritter 230kV #1 & #2: Construct SPDC with B-1272 | 2026-06-01 | Planned | Yemassee Substation | 32.6975 | -80.8639 | 32.6975 | -80.8639 | 24 | 4 | 10 | 10 | 3 | 51 | 8 | 2 | 3 | 1 | 96 | 20.9 | 8 | 6 | 0 | 220 | 6743000 | 3267000 | 4761000 | 631000 | 560000 | 1248000 | 17210000
0147 C, K | Cainhoy 115 kV Tap: Construct | 2027-12-31 | Planned | Cainhoy Substation | 32.9414 | -79.8423 | 32.9414 | -79.8423 | 21 | 4 | 5 | 6 | 5 | 41 | 6 | 1 | 2 | 1 | 54 | 11.1 | 1 | 4 | 0 | 204 | 5311000 | 2104000 | 2014000 | 577000 | 805000 | 2211000 | 13022000

## Notes
Workbook | Gridlock Utility A + Utility B Synthetic Resource Data
Utility A | 120 projects from the Utility A source dataset. Resource quantities and costs are synthetic prototype estimates.
Utility B | 7 projects supplied for Utility B. Resource quantities and costs are synthetic prototype estimates.
Cost Method | Total Project Cost = Labor + Equipment/Machinery + Material + Logistics + Engineering/Admin + External Contract Cost.
Important | Project IDs/names/source fields are preserved; added resource and financial values are sample/demo data, not actual utility internal figures.

## Collaboration Savings
Overlap ID | Utility A Project ID | Utility A Project | A In-Service Date | Utility B Project ID | Utility B Project | B In-Service Date | Distance (mi) | Time Gap (days) | Opportunity Type | A Total Project Cost ($) | B Total Project Cost ($) | Baseline Separate Cost ($) | A Equipment Cost ($) | B Equipment Cost ($) | A Logistics Cost ($) | B Logistics Cost ($) | A Contract Cost ($) | B Contract Cost ($) | A Material Cost ($) | B Material Cost ($) | Shared Bucket Trucks | Shared Digger Derricks | Shared Cranes | Shared Excavators | Distance Factor | Time Factor | Equipment Savings ($) | Logistics Savings ($) | Contract Savings ($) | Bulk Material Savings ($) | Estimated Potential Savings ($) | Estimated Collaborative Cost ($) | Savings % | Recommendation
OVL_1 | 20509 | CC - EMBLEM RIVERSIDE CUSTOMER SUB (FLEXENTIAL) | 03/01/2027 | 6808 S | Okatie-Bluffton 115kV: Rebuild | 06/01/2025 | 17.64 | 638 | Resource planning | 7578000 | 11757000 | 19335000 | 529000 | 1955000 | 464000 | 262000 | 2258000 | 2245000 | 1823000 | 2780000 | 6 | 1 | 0 | 1 | 80% | 50% | 42320 | 36680 | 107760 | 36460 | 223220 | 19111780 | 1.154% | Plan shared vendors/equipment where schedules can be adjusted
OVL_2 | 20067 | SAV: DEPTFORD - MAGNOLIA 115KV RECONDUCTOR | 06/01/2025 | 6808 S | Okatie-Bluffton 115kV: Rebuild | 06/01/2025 | 18.15 | 0 | Concurrent collaboration | 10094000 | 11757000 | 21851000 | 1673000 | 1955000 | 273000 | 262000 | 2326000 | 2245000 | 1917000 | 2780000 | 7 | 3 | 1 | 2 | 80% | 100% | 267680 | 73360 | 215520 | 76680 | 633240 | 21217760 | 2.898% | Highest priority: coordinate schedule, staging, equipment and procurement
OVL_3 | 20066 | SAV: BOULEVARD - DEPTFORD 115KV RECONDUCTOR | 06/01/2026 | 6808 S | Okatie-Bluffton 115kV: Rebuild | 06/01/2025 | 18.94 | 365 | Near-term coordination | 8053000 | 11757000 | 19810000 | 1077000 | 1955000 | 536000 | 262000 | 1300000 | 2245000 | 1548000 | 2780000 | 3 | 2 | 1 | 2 | 80% | 75% | 129240 | 55020 | 93600 | 46440 | 324300 | 19485700 | 1.637% | Strong candidate: align procurement, contractors and equipment mobilization
OVL_4 | 20407 | SAV: MAGNOLIA - TRUMAN PARKWAY 115KV REBUILD | 06/01/2028 | 6808 S | Okatie-Bluffton 115kV: Rebuild | 06/01/2025 | 20.03 | 1096 | Low timing alignment | 8390000 | 11757000 | 20147000 | 765000 | 1955000 | 471000 | 262000 | 2577000 | 2245000 | 1866000 | 2780000 | 6 | 2 | 0 | 2 | 60% | 10% | 9180 | 5502 | 16164 | 5598 | 36444 | 20110556 | 0.1809% | Primarily use visibility to prevent future duplication
OVL_5 | 20277 | SAV: MCINTOSH - PURRYSBURG 230KV REACTORS | 06/01/2026 | 6808 S | Okatie-Bluffton 115kV: Rebuild | 06/01/2025 | 20.45 | 365 | Near-term coordination | 14771000 | 11757000 | 26528000 | 2270000 | 1955000 | 582000 | 262000 | 1324000 | 2245000 | 2503000 | 2780000 | 5 | 3 | 1 | 2 | 60% | 75% | 175950 | 41265 | 71496 | 56317.5 | 345028.5 | 26182971.5 | 1.301% | Strong candidate: align procurement, contractors and equipment mobilization
OVL_6 | 21006 | SAV: BOULEVARD - MAGNOLIA 115 KV LINE REBUILD | 06/01/2029 | 6808 S | Okatie-Bluffton 115kV: Rebuild | 06/01/2025 | 20.78 | 1461 | Low timing alignment | 9266000 | 11757000 | 21023000 | 1629000 | 1955000 | 329000 | 262000 | 2400000 | 2245000 | 1256000 | 2780000 | 7 | 1 | 1 | 2 | 60% | 10% | 19548 | 5502 | 16164 | 3768 | 44982 | 20978018 | 0.214% | Primarily use visibility to prevent future duplication
OVL_7 | 20783 | SAV: COLEMAN - DEAN FOREST 115KV LINE REBUILD | 06/01/2028 | 6808 S | Okatie-Bluffton 115kV: Rebuild | 06/01/2025 | 22.86 | 1096 | Low timing alignment | 7614000 | 11757000 | 19371000 | 1158000 | 1955000 | 423000 | 262000 | 1427000 | 2245000 | 1462000 | 2780000 | 6 | 3 | 1 | 1 | 60% | 10% | 13896 | 5502 | 10274.4 | 4386 | 34058.4 | 19336941.6 | 0.1758% | Primarily use visibility to prevent future duplication
Savings Model Assumptions | Value
Equipment sharing rate | 20% of smaller equipment cost × distance factor × time factor
Logistics/staging sharing rate | 35% of smaller logistics cost × distance factor × time factor
Contractor coordination rate | 12% of smaller external contract cost × distance factor × time factor
Bulk material/procurement rate | 5% of smaller material cost × distance factor × time factor
Distance factor | ≤10 mi = 100%; ≤20 mi = 80%; ≤25 mi = 60%; >25 mi = 0%
Time factor | 0 days = 100%; ≤365 = 75%; ≤730 = 50%; ≤1095 = 25%; >1095 = 10%
Important | All savings are synthetic prototype estimates for demonstrating Gridlock's planning value; not actual utility savings commitments.